## Product_backlog
Project Name | Agile Manifesto Web Platform
StakeHolders/Customers/Users | abc/xyz/zxc etc.
Created By | Adlin Teenu
Epic | User Story ID | Feature/Title | User Story | Status | Acceptance Criteria
Create a web-based platform to educate and engage users about the Agile Manifesto | US001 | Homepage for Agile Manifesto | Design and implement a visually appealing homepage | New | Homepage is visually appealing and links to all main sections
| US002 | Homepage for Agile Manifesto | Add an introduction to Agile and its history | New | Introduction provides a concise history of Agile.
| US003 | Homepage for Agile Manifesto | Include navigation to other sections of the platform | New | Navigation links to Agile Values, Resource Library, Collaboration Features.
| US004 | Agile Values and Principles | Create a page to display the four core Agile values | New | Page displays values clearly with explanations.
| US005 | Agile Values and Principles | Implement an interactive feature to explain the 12 principles | New | Interactive feature is functional and engaging.
| US006 | Agile Values and Principles | Add examples to illustrate each value and principle | New | Each value and principle has relevant examples.
| US007 | Resource Library | Design a library for Agile practices (e.g., Scrum, Kanban) | New | Library includes links to Agile practices.
| US008 | Resource Library | Include downloadable resources like templates and guides | New | Resources are accessible and downloadable.
| US009 | Resource Library | Add search and filter functionality | New | Search and filter work seamlessly.
| US010 | Collaboration Features | Develop a discussion forum for users | New | Forum is functional and allows user interaction.
| US011 | Collaboration Features | Enable users to comment on resources and principles | New | Comments can be added and stored.
| US012 | Collaboration Features | Implement user authentication for collaboration features | New | Users can register and log in securely.

## Spring_planning
Project Name | Agile Manifesto Web Platform
StakeHolders/Customers/Users | abc/xyz/zxc etc.
Created By | Adlin Teenu
Epic | User Story ID | Feature/Title | User Story | Story Points | Sprint
Create a web-based platform to educate and engage users about the Agile Manifesto | US001 | Homepage for Agile Manifesto | Design and implement a visually appealing homepage | 5 | 1
| US002 | Homepage for Agile Manifesto | Add an introduction to Agile and its history | 3 | 1
| US003 | Homepage for Agile Manifesto | Include navigation to other sections of the platform | 2 | 1
| US004 | Agile Values and Principles | Create a page to display the four core Agile values | 3 | 2
| US005 | Agile Values and Principles | Implement an interactive feature to explain the 12 principles | 5 | 2
| US006 | Agile Values and Principles | Add examples to illustrate each value and principle | 3 | 2
| US007 | Resource Library | Design a library for Agile practices (e.g., Scrum, Kanban) | 8 | 3
| US008 | Resource Library | Include downloadable resources like templates and guides | 5 | 3
| US009 | Resource Library | Add search and filter functionality | 8 | 3
| US010 | Collaboration Features | Develop a discussion forum for users | 13 | 4
| US011 | Collaboration Features | Enable users to comment on resources and principles | 8 | 4
| US012 | Collaboration Features | Implement user authentication for collaboration features | 13 | 4

## Tasks
QA Tasks | Developer Tasks
Reviewing User Stories | Reviewing User Stories
Creating Test Cases | Setting up Development Environment
Setting up Test Environment | Developing Programs
Executing Manual Tests | Code Review
Creating Test Data | Creating Unit Test Cases
Creating wireframes for features | Implementing frontend and backend code
Testing interactive features | Debugging and resolving issues
Performing integration testing | Integrating APIs